## Backlog
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | story points
1 | usage | user | click on a button on an Android device | I can switch a Led-GUI on a PC |  |  | 1 | 10 | As a / an user I want to click on a button on an Android device so that I can switch a Led-GUI on a PC
2 | personalisaton | user | have a Led-mirror on Andorid | I can have a picture of the Led-Gui state |  |  | 2 | 20 | As a / an user I want to have a Led-mirror on Andorid so that I can have a picture of the Led-Gui state
|  |  | move the Led on Arduino | I can work on a real Led
|  |  | move the Led on Raspberry | I can work on a real Led in another technology

## Done
id | theme | as a/an | I want to… | so that… | notes | acceptance criteria | added in sprint | closed in sprint | story points
1 | usage | user | view the led changing its state | I can see the system working as a concentrate system |  |  | 1 | 1 | 30 | As a / an user I want to view the led changing its state so that I can see the system working as a concentrate system
2 | personalisation | user | be able to select the LED | I can see the system working as a distributed system |  |  | 2 | 2 | 70 | As a / an user I want to be able to select the LED so that I can see the system working as a distributed system

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
0 | 100 | 0 | 0 | 0% | 0 | 100
1 | 70 | 30 | 0 | 30% | 0 | 70
2 | 0 | 70 | -30 | 100% | 30 | 30
3
4
5
6
7
8
9
10

## Lists
0
5
10
20
30
50
80
130
200
400
1000